## Phase-1 Extension-Additional
Funtionality | Release | Design Date |  | Development Date |  | UAT Date |  | Release Date
|  | St Date | End Date | St Date | End Date | St Date | End Date | St Date | End Date
Refine search | I | 2015-12-07 | 2015-12-11
Search bar redesign
Info Page additional Tabs
Facilities & Inf Board
Analytics Details in Info Page
Similar nearby subdomain
Map Based Search | II | 2015-12-10 | 2015-12-16
Compare Result
Online Registration
Ask a Question | III | 2015-12-14 | 2015-12-18
Add to wishlist
iDiksha Ratings
Get Contact details as SMS
Want To suggest Edit
Facebook Promotion design
Link To Discussion form thread
SMS Integration
Chat Messagener

## Sheet2
Phase1-Extension-Estimate
No. Of Day | Cost
22 | 50000
16 | 36363.6364
38 | 86363.6364