## Sheet1
Project Name: SchoolPro.com
Test case Id | Module Name | Test Title | Test Steps | Test Data | Priority | Severity | Expected Result | Actual Result | Status | Remark | Developer Comment
1 | Register | User Registration page | Check the color and size of the asterisk mark |  | low | Minor | Should be in red color Increase the size of the asterisk | Asterisk mark is in black color size is very small | Partial | 1.Change to red color- fixed 2.Increase the size of the star mark
2 | Register | User Registration page | Text alignment |  | low | Minor |  |  | Pass | Align the text to centre of the box-fixed
3 | Register | User Registration page | Click on terms and condtions button |  | low | Minor | the color of the button should remain in red color | The color of the button is changed to black. | Pass | Keep the button color in red- fixed
4 | Register | User Registration | Fill the registration form and click on register button.Refresh the page then close the page. Again login to the application and goto the registration page. |  | Medium | Minor | The contents of the older registerd details should not be present | The older registered details are present in the page |  | Delete the old details. It should not be shown. | this you find only if registration failed.
5 | Register | User Registration | Colon infront of the fields |  | Low | Minor |  |  |  | Remove the colon from infront of the text
6 | Register | Registrater Button | Click on Register button |  | Register button should not disappear | Register button is disappearing | High | Minor | Fail |  | It is right
7 | Login | Login page verification | In the login page click on register now button |  | should display register page | Register page is not displaying. Instead of the register page create an account page is displaying in small size. | High | Moderate | pass | Fixed | We have removed that text itself
8 | Login | Login page verification | Asterisk Mark |  | Should be in red color | Asterisk mark is not in red color | Low | Minor | partial | 1.Change the color from black to red 2.Increase the size of the star mark
9 | Login | Login page verification | Enter invalid username and password | Username:aaa password:111 | Should display error message | Error message is not displaying. | High | Major | Fail | Not fixed | Displays error message
10 | Login | Login page verification | Enter valid username and invalid password |  | Should display error message | Error message is not displaying. | High | Major | Fail | Not fixed | Displays error message
11 | Login | Login page verification | Enter invalid username and valid password |  | Should display error message | Error message is not displaying. | High | Major | Fail | Not fixed | Displays error message